## RTM
Requirements_Traceability_Matrix
ID | Ass. ID | Requirements Description | Business Need, Justification | Project Objective | Requested By | Department | WBS Element | Specification | Design | Test Cases
1 | 1.1 | User Login with JWT | Secure access to protected features and role dashboards | Build secure authentication foundation | Project Guide | Technical | 1 | Finished | Finished | TC-001
1 | 1.2 | User Registration | Allow new participants to create accounts | Enable self-service onboarding | Student Users | Student Affairs | 1.1 | Finished | Finished | TC-002, TC-003
1 | 1.3 | Role-Based Access Control | Restrict host, organiser, management, user actions correctly | Enforce authorization and data safety | Admin Team | Technical | 1.2 | Finished | Finished | TC-004, TC-005
2 | 2.1 | Host Creates Organiser Accounts | Centralized governance for organiser onboarding | Controlled admin hierarchy | Host | Administration | 2 | Finished | Finished | TC-006
2 | 2.2 | Organiser Creates Management Users | Delegate operations for events | Improve event execution efficiency | Organiser | Event Operations | 2.1 | Finished | Finished | TC-007
3 | 3.1 | Main Event CRUD | Manage umbrella events with date windows | Support annual/festival event planning | Organiser | Event Operations | 3 | Finished | Finished | TC-008, TC-009
3 | 3.2 | Sub-Event CRUD | Manage competitions/workshops under each main event | Granular event management | Management Team | Event Operations | 3.1 | Finished | Finished | TC-010, TC-011
4 | 4.1 | Team Creation for Team Events | Support collaborative participation | Enable team-based competitions | Student Users | Student Affairs | 4 | Finished | Finished | TC-012
4 | 4.2 | Team Member Add/Remove | Allow leader-controlled team updates | Keep team composition accurate | Team Leaders | Student Affairs | 4.1 | Finished | Finished | TC-013, TC-014
5 | 5.1 | Individual Event Registration | Let users register quickly for solo events | Increase participation and reduce manual work | Student Users | Event Operations | 5 | Finished | Finished | TC-015
5 | 5.2 | Team Event Registration | Allow leader to register team to an event | End-to-end team participation flow | Team Leaders | Event Operations | 5.1 | Finished | Finished | TC-016, TC-017
5 | 5.3 | Registration Uniqueness Validation | Prevent duplicate registrations | Preserve data integrity | Technical Lead | Technical | 5.2 | Finished | Finished | TC-018
6 | 6.1 | Registration View by User | Show all registrations with status to participant | Improve transparency and user confidence | Student Users | Student Affairs | 6 | Finished | Finished | TC-019
6 | 6.2 | Event-wise Registrations for Organiser/Management | Track participant lists by event for operations | Support event-day execution and verification | Organiser | Event Operations | 6.1 | Finished | Finished | TC-020
7 | 7.1 | AI Chatbot for Event Queries | Provide instant help for event details and registration guidance | Reduce support load and improve UX | Project Team | Support | 7 | Finished | Finished | TC-021, TC-022
8 | 8.1 | Health Endpoint | Quick availability check for backend | Improve reliability monitoring | Technical Lead | Technical | 8 | Finished | Finished | TC-023
9 | 9.1 | Static Role Dashboards and Navigation | Separate dashboards for host, organiser, management, user | Improve usability and task focus by role | Project Guide | UX/UI | 9 | Finished | Finished | TC-024, TC-025
10 | 10.1 | Email Integration for Notifications | Send operational notifications from system account | Communication automation | Administration | Support | 10 | In Progress | In Progress | TC-026