## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 112
| Number of testers | 1
| Test cycle duration | 2 days
Status for Day 1
| Number of test cases planned | 56
| Number of test cases executed | 53
| Number of test cases executed overall | 48
| Number of defects encountered today | 5 | Status for Day 2
| Number of defect encountered so far | 7
| Number of critical defects- still open | 2 | Number of test cases planned | 56
|  |  | Number of test cases executed | 53
|  |  | Number of test cases executed overall | 49
|  |  | Number of defects encountered today | 4
Overall status |  |  | Number of defect encountered so far | 5
| Number of test cases planned | 112 | Number of critical defects- still open | 1
| Number of test cases executed | 106
| Pass Percentage of the defects | 91.5%
| Defects density | 6 per day
| Critical defects percentage | 25%

## Detailed status
Module | Scenarios | Sub Levels | Complexity | Responsible Tester | Date of Execution | Status(Pass/Fail/Blocked/Not Executed) | Defect ID - Brief Description | Severity | Defect Status
Authentication | JWT Login | Valid Admin Login | Medium | Tester A | 04/05/2026 | Pass
Authentication | JWT Login | Invalid Password Handling | Medium | Tester A | 04/05/2026 | Pass
Authentication | RBAC Validation | Admin Route Protection | Complex | Tester A | 04/05/2026 | Pass
Authentication | RBAC Validation | Unauthorized Dashboard Access | Complex | Tester A | 04/05/2026 | Fail | 3001: Analytics endpoint accessible before token refresh under session timeout edge case. | 1- High | Open
API Gateway | Request Validation | Zod Schema Validation | Medium | Tester A | 04/05/2026 | Pass
API Gateway | Kafka Publish | Allocation Request Publish | Complex | Tester A | 04/05/2026 | Pass
API Gateway | Kafka Publish | Retry Handling During Broker Delay | Complex | Tester A | 04/05/2026 | Blocked | 3002: Kafka retry verification blocked due to intermittent local broker disconnect. | 2- Medium | Blocked
Kafka Engine | Consumer Processing | Concurrent Request Consumption | Complex | Tester A | 04/05/2026 | Pass
Kafka Engine | Consumer Processing | Burst Load Processing (>40 req) | Complex | Tester A | 04/05/2026 | Fail | 3003: Consumer lag increased significantly during burst load simulation. | 1- High | Assigned
Redis Cache | Cache Retrieval | Resource Availability Fetch | Medium | Tester A | 04/05/2026 | Pass
Redis Cache | Cache Sync | Rapid Allocation Synchronization | Complex | Tester A | 04/05/2026 | Fail | 3004: Stale cache values returned during rapid sequential allocations. | 2- Medium | Assigned
MongoDB | Persistence | Allocation Record Storage | Medium | Tester A | 04/05/2026 | Pass
MongoDB | Persistence | Rejected Request Logging | Medium | Tester A | 04/05/2026 | Pass
AI Support Engine | Feasibility Prediction | Prediction Consistency | Complex | Tester A | 04/05/2026 | Pass
AI Support Engine | Load Prediction | High Queue Prediction | Complex | Tester A | 04/05/2026 | Pass
AI Support Engine | Priority Scoring | Priority Ranking Under Load | Complex | Tester A | 04/05/2026 | Fail | 3005: Priority scoring latency exceeded threshold during sustained queue load. | 2- Medium | Open
Allocation Engine | Greedy Allocation | Best Resource Selection | Complex | Tester A | 04/05/2026 | Pass
Allocation Engine | Conflict Prevention | Duplicate GPU Allocation Check | Complex | Tester A | 04/05/2026 | Pass
Allocation Engine | Queue Scheduling | Priority Queue Handling | Complex | Tester A | 04/05/2026 | Pass
WebSocket | Realtime Updates | Allocation Status Broadcast | Medium | Tester A | 04/05/2026 | Pass
WebSocket | Reconnect Handling | Rapid Reconnection Simulation | Medium | Tester A | 04/05/2026 | Fail | 3006: WebSocket reconnection delay observed after server restart. | 2- Medium | Assigned
Frontend UI | Dashboard | Analytics KPI Rendering | Medium | Tester A | 04/05/2026 | Pass
Frontend UI | Dashboard | Global Admin Analytics | Complex | Tester A | 05/05/2026 | Fail | 3007: Partial tenant aggregation displayed in admin analytics dashboard. | 1- High | Open
Frontend UI | Request Submission | Preferred Resource Selection | Medium | Tester A | 05/05/2026 | Pass
Frontend UI | Request Submission | Validation Error Rendering | Medium | Tester A | 05/05/2026 | Pass
Monitoring | Prometheus Metrics | Metrics Scraping | Medium | Tester A | 05/05/2026 | Pass
Monitoring | Grafana Dashboard | Realtime Panel Refresh | Medium | Tester A | 05/05/2026 | Pass
Monitoring | Alerting | Queue Threshold Alert | Complex | Tester A | 05/05/2026 | Not Executed
Authentication | JWT Login | Valid Admin Login - Regression | Medium | Tester A | 05/05/2026 | Pass
Authentication | JWT Login | Invalid Password Handling - Regression | Medium | Tester A | 05/05/2026 | Pass
Authentication | RBAC Validation | Admin Route Protection - Regression | Complex | Tester A | 05/05/2026 | Pass
Authentication | RBAC Validation | Unauthorized Dashboard Access - Regression | Complex | Tester A | 05/05/2026 | Fail | 3001: Analytics endpoint accessible before token refresh under session timeout edge case. | 1- High | Assigned
API Gateway | Request Validation | Zod Schema Validation - Regression | Medium | Tester A | 05/05/2026 | Pass
API Gateway | Kafka Publish | Allocation Request Publish - Regression | Complex | Tester A | 05/05/2026 | Pass
API Gateway | Kafka Publish | Retry Handling During Broker Delay - Regression | Complex | Tester A | 05/05/2026 | Blocked | 3002: Kafka retry verification blocked due to intermittent local broker disconnect. | 2- Medium | Blocked
Kafka Engine | Consumer Processing | Concurrent Request Consumption - Regression | Complex | Tester A | 05/05/2026 | Pass
Kafka Engine | Consumer Processing | Burst Load Processing (>40 req) - Regression | Complex | Tester A | 05/05/2026 | Fail | 3003: Consumer lag increased significantly during burst load simulation. | 1- High | Assigned
Redis Cache | Cache Retrieval | Resource Availability Fetch - Regression | Medium | Tester A | 05/05/2026 | Pass
Redis Cache | Cache Sync | Rapid Allocation Synchronization - Regression | Complex | Tester A | 05/05/2026 | Fail | 3004: Stale cache values returned during rapid sequential allocations. | 2- Medium | Assigned
MongoDB | Persistence | Allocation Record Storage - Regression | Medium | Tester A | 05/05/2026 | Pass
MongoDB | Persistence | Rejected Request Logging - Regression | Medium | Tester A | 05/05/2026 | Pass
AI Support Engine | Feasibility Prediction | Prediction Consistency - Regression | Complex | Tester A | 05/05/2026 | Pass
AI Support Engine | Load Prediction | High Queue Prediction - Regression | Complex | Tester A | 05/05/2026 | Pass
AI Support Engine | Priority Scoring | Priority Ranking Under Load - Regression | Complex | Tester A | 05/05/2026 | Fail | 3005: Priority scoring latency exceeded threshold during sustained queue load. | 2- Medium | Assigned
Allocation Engine | Greedy Allocation | Best Resource Selection - Regression | Complex | Tester A | 05/05/2026 | Pass
Allocation Engine | Conflict Prevention | Duplicate GPU Allocation Check - Regression | Complex | Tester A | 05/05/2026 | Pass
Allocation Engine | Queue Scheduling | Priority Queue Handling - Regression | Complex | Tester A | 06/05/2026 | Pass
WebSocket | Realtime Updates | Allocation Status Broadcast - Regression | Medium | Tester A | 06/05/2026 | Pass
WebSocket | Reconnect Handling | Rapid Reconnection Simulation - Regression | Medium | Tester A | 06/05/2026 | Fail | 3006: WebSocket reconnection delay observed after server restart. | 2- Medium | Assigned
Frontend UI | Dashboard | Analytics KPI Rendering - Regression | Medium | Tester A | 06/05/2026 | Pass

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
3001 | Admin analytics endpoint becomes accessible briefly before JWT token refresh validation completes. | 1. Login using a low-privilege user account 2. Keep the session idle until token expiration 3. Refresh the analytics dashboard immediately after expiration 4. Observe API response before automatic token refresh completes Expected Result: Unauthorized users should never access admin analytics routes. Actual Result: A short-lived access window exposes partial analytics data before the RBAC middleware blocks the request. | 1- High | Open | Tester A | Backend API Team
3002 | Kafka consumer lag increases significantly during burst request simulation. | 1. Start the Schedulord allocation services 2. Simulate more than 40 concurrent allocation requests 3. Monitor Kafka consumer processing time 4. Observe queue growth and delayed consumption Expected Result: Requests should be consumed within acceptable latency thresholds. Actual Result: Consumer lag spikes under burst load conditions causing delayed allocation updates. | 1- High | Assigned | Tester A | Streaming Team
3003 | Redis cache returns stale resource availability data during rapid sequential allocations. | 1. Submit multiple GPU allocation requests simultaneously 2. Trigger rapid allocation and release cycles 3. Refresh the resource dashboard repeatedly 4. Compare dashboard data with MongoDB records Expected Result: Redis cache should reflect latest allocation state. Actual Result: Some cached resource states remain outdated for several seconds. | 2- Medium | Assigned | Tester A | Cache Management Team
3004 | WebSocket reconnection delay observed after backend restart simulation. | 1. Open the live allocation dashboard 2. Restart the API Gateway service 3. Observe WebSocket reconnection behavior 4. Track delay before updates resume Expected Result: Realtime updates should reconnect automatically within acceptable time. Actual Result: UI remains disconnected for extended duration before updates resume. | 2- Medium | Open | Tester A | Realtime Communication Team
3005 | AI priority scoring latency exceeds threshold during sustained queue load. | 1. Populate allocation queue with more than 100 requests 2. Enable AI support pipeline 3. Observe scoring and allocation timings 4. Compare latency against baseline execution Expected Result: Priority scoring should remain within real-time processing threshold. Actual Result: Scoring latency increases noticeably during prolonged high-load conditions. | 2- Medium | In Progress | Tester A | AI Support Team
3006 | Frontend analytics dashboard displays incomplete tenant aggregation for administrators. | 1. Login using administrator account 2. Navigate to global analytics dashboard 3. Compare tenant counts against database records 4. Refresh dashboard multiple times Expected Result: All tenant statistics should load correctly. Actual Result: Some tenant metrics intermittently fail to render in the dashboard. | 1- High | Open | Tester A | Frontend Team
3007 | Allocation response time exceeds 2.5 seconds under heavy queue conditions. | 1. Simulate more than 120 concurrent allocation requests 2. Monitor allocation engine processing time 3. Compare allocation completion timestamps 4. Observe queue scheduling behavior Expected Result: Allocation responses should remain below defined SLA threshold. Actual Result: Response time exceeds acceptable latency during high queue pressure. | 2- Medium | Assigned | Tester A | Core Engine Team
3008 | Prometheus metrics scraping interval mismatch causes temporary dashboard inconsistency. | 1. Open Grafana monitoring dashboard 2. Trigger high allocation activity 3. Observe Prometheus scrape intervals 4. Compare live values against actual engine metrics Expected Result: Dashboard metrics should remain synchronized. Actual Result: Temporary inconsistencies appear between actual and displayed metrics. | 3- Low | Open | Tester A | Monitoring Team